OFFICIAL

# EFIQ Connectathon 2026
Track 2 External Service Access Investigation

Hosting, network accessibility and Queensland Health participant device readiness

Prepared 22 September 2026
Decision-support report and verification plan

Status: CONDITIONAL GO The scenario is technically feasible, but it is not yet proven for the 2026 venue and Queensland Health managed laptops. Proceed with publicly reachable, HTTPS-only hosted services and a browser-first participant path, subject to an on-site pre-flight test and written confirmation of network and endpoint constraints.

# Executive summary

Track 2 intends to use externally hosted example services from Queensland Health laptops. The strongest delivery model is a centrally hosted, non-production environment exposed through public DNS and trusted HTTPS on TCP 443. Participants should be able to complete the core activities in a standard browser. Postman, command-line tools and local development environments should be treated as optional enhancements rather than prerequisites.

The available evidence shows that the 2025 Queensland Health Connectathon successfully advertised both secured and open external FHIR server URLs and instructed attendees to bring laptops, software and remote-access tools. This is encouraging precedent, but it does not prove that the 2026 venue network or current managed-laptop controls will permit all required endpoints, request methods or tools.

| Area | Current assessment | Decision condition |
| --- | --- | --- |
| Hosting | Feasible | Deploy reproducibly; use synthetic data; provide health checks, logs and rollback. |
| Venue/network | Unverified critical dependency | Test from the actual participant network using a representative QH laptop. |
| Participant devices | Browser likely safest; developer tooling unknown | Core workflow must require no installation or administrator rights. |
| Security/governance | Non-production only | No real patient data; minimise accounts; document retention and shutdown. |
| Resilience | Needs deliberate preparation | Load test, monitor dependencies and provide a fallback endpoint or degraded mode. |

# 1. Scope and evidence base

This report addresses: (1) hosting the example services; (2) ensuring they are reachable from the network used by participants; and (3) ensuring Queensland Health laptop operating systems, browsers and approved software permit the required interactions.

Track 2 meeting material identifies network access, laptop restrictions, cloud hosting and reliable backend connectivity as immediate technical blockers.

The proposed experience is a hosted tutorial-style demonstrator with HL7v2 submission, transformation, validation, logging and FHIR consumption.

The anticipated audience is mixed, so the core learning path cannot assume developer privileges or locally installed infrastructure.

Public Queensland Health policy material establishes risk-based ICT governance and mandatory controls, but the detailed device and external-access settings applicable to the participants are not publicly determinable.

The 2025 event provides practical precedent for external open and secured FHIR endpoints, but not assurance for 2026.

# 2. Recommended target architecture

Design principle Centralise complexity. Participants interact over HTTPS; organisers operate the container platform, databases, terminology dependencies, observability and recovery controls.

| Layer | Recommended design | Rationale |
| --- | --- | --- |
| Participant | Supported browser; optional Postman/curl/IDE | Avoid installation and administrator-right dependencies. |
| Edge | Public DNS, CA-issued TLS, HTTPS 443, reverse proxy/WAF | Maximises compatibility with managed networks and enables traffic controls. |
| Experience | Web launcher, guided exercises, API console, status page | Allows clinical and non-developer participation. |
| Services | HL7v2 receiver, transformer/validator, FHIR server, provider/service API | Matches the proposed Track 2 workflow while remaining modular. |
| Data | Synthetic test data only; scheduled reset | Avoids handling real health information and preserves repeatability. |
| Operations | Central logs, metrics, health probes, request correlation IDs | Supports rapid diagnosis during the event. |
| Fallback | Second endpoint or static/degraded demonstrator | Prevents a single backend or dependency failure stopping the track. |

# 3. Hosting options

| Option | Advantages | Risks / constraints | Recommendation |
| --- | --- | --- | --- |
| Existing FHIRLab/shared cloud | Existing operational patterns and reusable container recipes | Shared dependencies, service cost and availability need confirmation | Preferred if capacity and governance owners approve. |
| Dedicated public cloud environment | Isolation, reproducibility and clearer event ownership | Setup, cost, DNS/certificate and operational burden | Strong alternative; keep architecture minimal. |
| Queensland Health internal hosting | Potentially aligns with internal network controls | Governance, lead time, access and operational dependencies | Use only if already available and sponsored. |
| Participant-local containers | Offline-capable and developer-controlled | Likely blocked by permissions, Docker/WSL availability and mixed audience | Not suitable as the primary path. |
| Single laptop/server in room | Simple contingency for a small group | Wi-Fi routing, firewall, discovery and single-point failure | Emergency fallback only, pre-tested on venue network. |

# 4. Network accessibility

The make-or-break test is not generic internet access. It is whether a representative Queensland Health laptop, connected to the exact event network, can resolve the names, trust the certificates, perform the required HTTP methods and receive expected responses without proxy, filtering, TLS inspection, authentication or cross-origin failures.

| Test | Method | Pass criterion |
| --- | --- | --- |
| DNS | Resolve every production and fallback hostname | Consistent public resolution from the event network. |
| TLS | Open endpoints in supported browser; inspect certificate chain | No warning, interception failure or untrusted issuer. |
| HTTP read | GET capability statement/status resource | Expected 200 response and content. |
| HTTP write | POST/PUT synthetic resource or message | Expected success or deliberate FHIR validation response, not network/proxy failure. |
| Browser CORS | Run the actual browser client against APIs | Pre-flight and API calls succeed for approved origins. |
| Authentication | Complete the chosen login/token flow | No blocked redirects, third-party cookies or inaccessible identity endpoint. |
| Streaming, if used | Exercise WebSocket/SSE logging view | Connection remains stable; otherwise use polling. |
| Downloads | Retrieve exercise files and example payloads | Files are not blocked or quarantined beyond usable limits. |
| Performance | Run expected concurrent scripted workload | Response times and error rates remain within the workshop acceptance threshold defined before testing. |

# 5. Participant software and operating-system readiness

| Capability tier | Required software | Activities |
| --- | --- | --- |
| Tier A: all participants | Supported browser only | Use guided UI, submit synthetic examples, view transformations, query curated resources and inspect results. |
| Tier B: technical users | Browser plus approved Postman or equivalent | Direct REST requests, modify payloads, inspect headers and validation responses. |
| Tier C: small developer group | Approved IDE, Git and runtime/toolchain as confirmed | Build or modify clients and services; organisers must coordinate these participants before the event. |
| Organiser tier | Managed cloud/admin access on organiser devices | Deployment, monitoring, resets and incident response. Do not depend on QH participant devices for operations. |

Do not require Docker Desktop, WSL, Hyper-V, local databases, inbound ports, local administrator rights or unsigned executables for the core path.

Provide browser-based alternatives for API exploration and payload editing.

Publish a short compatibility list for browser versions and optional tools after representative-device testing.

Prepare copy-and-paste examples, downloadable synthetic payloads and a no-install troubleshooting path.

# 6. Security, privacy and governance controls

Use synthetic or explicitly de-identified workshop data only. Display this rule in the UI and participant instructions.

Classify the environment as non-production and separate it from operational Queensland Health systems.

Expose only necessary endpoints; keep databases and administrative interfaces private.

Use trusted HTTPS, least-privilege accounts, short-lived event credentials where authentication is required, and remove credentials after the event.

Define data reset, log retention and environment shutdown dates before launch.

Do not assume a publicly reachable service is approved merely because it is technically accessible. Record the QH event/network owner and the service-risk owner.

# 7. Authentication decision

| Pattern | When to use | Trade-off |
| --- | --- | --- |
| Anonymous synthetic sandbox | Exercises need no user identity and contain no sensitive data | Lowest friction; requires rate limits, reset and abuse controls. |
| Shared event credentials | Simple access separation is needed | Operationally easy but weak attribution and credential leakage risk. |
| Pre-provisioned individual accounts | Identity-dependent exercises or auditability are required | More support overhead; test account recovery and MFA at venue. |
| Federated QH identity | Only if formally supported and tested | Best organisational fit, highest integration and approval risk for a short event. |

# 8. Reliability and operational readiness

Freeze deployable versions before the event and redeploy the complete environment from source-controlled configuration.

Use automated smoke tests for DNS, TLS, read, write, validation and terminology dependencies.

Monitor externally from the same path participants use, not only from inside the cloud environment.

Pre-warm caches and terminology content used by exercises.

Provide a visible service-status page and a one-page incident runbook with owners and fallback actions.

Keep a clean reset snapshot or scripted reseed so workshop state can be restored between sessions.

Avoid dependence on public reference terminology services where timeout or availability is outside the track team’s control; test every transitive dependency.

# 9. Pre-flight verification plan

| When | Activity | Owner role | Evidence |
| --- | --- | --- | --- |
| As soon as endpoint names exist | Submit domains, IP ranges and purpose for QH/network review if required | Track technical lead + QH ICT contact | Written disposition and ticket/reference. |
| Before participant guidance is final | Test actual QH laptop/browser and optional tools | QH representative participant | Completed compatibility checklist with screenshots/logs. |
| At venue before event | Repeat full test on the exact participant Wi-Fi/network | Track lead + venue/network contact | Signed pre-flight record. |
| Before event | Load and soak test the complete workflow, including dependencies | Hosting operator | Test report and accepted thresholds. |
| Before each day | Run automated smoke tests and reseed synthetic data | Operations owner | Timestamped pass/fail report. |
| During event | Monitor errors, latency, capacity and dependency health | Operations owner | Dashboard and incident log. |
| After event | Export approved artefacts, remove credentials and shut down/reset | Service owner | Closure checklist. |

# 10. Go/no-go decision gates

| Gate | Go criterion | If not met |
| --- | --- | --- |
| G1 Hosted environment | Reproducible deployment; endpoints and dependencies healthy | Simplify service set or use existing proven environment. |
| G2 QH network | Representative laptop passes DNS/TLS/GET/POST/PUT/browser tests on event network | Arrange allow-listing, alternate network or host internally. |
| G3 Core participant path | All core exercises work in browser without installation | Redesign exercises; do not rely on developer tooling. |
| G4 Developer extension | Named developer devices have confirmed approved toolchains | Limit extension work to organiser-managed environment. |
| G5 Security/privacy | Synthetic data rule, access model, retention and owner approved | Do not open the service. |
| G6 Reliability | Load test, monitoring, reset and fallback demonstrated | Reduce scope or postpone live dependency. |

Recommended decision Adopt a conditional-go posture now. Commit to the hosted, HTTPS-only, browser-first architecture, but do not declare readiness until G2 and G3 have been demonstrated on a representative Queensland Health laptop using the actual event network.

# 11. Questions requiring explicit confirmation

Which network will QH laptops use at the venue: corporate, guest, conference or another managed service?

Are arbitrary public HTTPS sites permitted, and is allow-listing required for new domains or cloud hosts?

Does TLS inspection affect API clients, WebSockets, certificate pinning or non-browser tools?

Which browsers and versions are deployed and supported?

Are Postman, VS Code, Git, curl/PowerShell, Node, Java, Python, Docker Desktop or WSL installed or installable?

Can participants use personally supplied devices or an alternate network if a managed device is blocked?

Are downloads, ZIP files, JSON files or executable scripts restricted?

Can OAuth/OIDC redirects, pop-ups and third-party identity endpoints be used?

Who can authorise network exceptions and who will be available during the event?

What concurrency and participant count should be used for the acceptance load test?

# 12. Proposed minimum viable implementation

One public HTTPS domain with path-based routing to the launcher, status page, message receiver, FHIR API and log/diagnostic view.

One centrally operated container environment with reproducible configuration and separate persistent/ephemeral data controls.

A browser-based exercise that submits only synthetic data and shows each processing stage.

Optional direct API exercises for participants whose approved tools work.

Automated smoke tests and a scripted reset/reseed process.

A fallback endpoint or demonstrator mode that preserves the teaching flow if a dependency fails.

# 13. Findings and limitations

The evidence supports technical feasibility and provides precedent for external FHIR endpoints at the previous event. It does not establish the exact 2026 QH laptop build, installed applications, permitted request methods, venue network policy or allow-listing process. Those items must be verified empirically and with the relevant Queensland Health and venue contacts. This report intentionally separates verified facts from recommended engineering controls.

# Appendix A. Representative-device test record

| Field | Result / notes |
| --- | --- |
| Device asset/build |  |
| Operating system/version |  |
| Browser/version |  |
| Network/SSID/VLAN |  |
| Proxy/TLS inspection observed |  |
| DNS test |  |
| TLS trust test |  |
| GET test |  |
| POST/PUT test |  |
| CORS test |  |
| Authentication test |  |
| Optional Postman/curl test |  |
| WebSocket/SSE test |  |
| Downloads test |  |
| Tester/date/location |  |
| Overall result: PASS / CONDITIONAL / FAIL |  |

# Appendix B. Source register

| Source | Use in this report |
| --- | --- |
| Track 2 meeting summary and transcript, 22 September 2026 | Track scope, hosted tutorial concept, audience, infrastructure risks and assigned actions. |
| Connectathon planning discussions, September 2026 | Hosting challenge, network/software questions and 2026 planning context. |
| 2025 FHIR in QH Connectathon programme and participant guide | Precedent for participant laptops, optional software and external open/secured FHIR endpoints. |
| Queensland Health ICT policies page and Use of ICT services and devices policy | Public policy context; detailed internal controls may require QH login. |
| Queensland Government Information and cyber security policy (IS18) | Risk-based security, ISMS and minimum control context. |
| Queensland Health BYOD self-managed service standard | Evidence that QH-managed access is controlled and risk-assessed; primarily mobile BYOD scope. |
| Internal FHIRLab Connectathon operational records | Hosting patterns, terminology dependency risks, automated testing and cost/availability lessons. |