# FHIR in QH Connectathon 2026

## Track 2 – FHIR for Services

### Meeting Summary and Actions

Meeting: Connectathon ideas
 Date: 22 September 2026
 Participants: Joern Guy Suess, Daniel Foulkes, Paul Davies
 Source: Meeting transcript and discussion outcomes. [Connectathon ideas | Meeting]

# Overview

The team reviewed the current direction of the FHIR for Services track and discussed whether a Provider Directory remains the most effective focus for the Connectathon.

A strong preference emerged for a practical, hands-on learning experience that demonstrates interoperability concepts through a guided HL7v2-to-FHIR workflow. The objective is to provide value to a mixed audience consisting of clinicians, project staff, architects, and developers while ensuring tangible outcomes can be achieved during the two-day event. [Connectathon ideas | Meeting]

# Proposed Connectathon Vision

Rather than focusing exclusively on Provider Directory implementation, the track may centre on a guided interoperability tutorial using a hosted HL7v2-to-FHIR solution.

Participants would:

- Generate or modify HL7v2 messages.

- Submit messages to a hosted integration endpoint.

- Observe validation and transformation processes.

- View resulting FHIR resources.

- Explore how data flows through an interoperability architecture.

- Extend or customise components where appropriate. [Connectathon ideas | Meeting]

Potential extension areas include:

- Imaging and RIS integration

- Appointment workflows

- Provider Directory integration

- FHIR profiling and implementation guides

- Front-end applications

- Message transformation and validation

- FHIR search and REST interactions [Connectathon ideas | Meeting]

# Draft Tutorial Architecture

## Participant Experience

### Stage 1 – Message Creation

Participants interact with a simple user interface to:

- Create HL7v2 messages

- View message structure

- Understand how messages are assembled

### Stage 2 – Message Submission

Messages are submitted to a hosted receiver service where participants can:

- Observe transmission

- View processing activities

- Explore validation outcomes

### Stage 3 – FHIR Transformation

The platform transforms incoming messages into FHIR resources using predefined mappings and validation logic.

### Stage 4 – Application Consumption

Participants view resulting data through:

- A FHIR server

- REST queries

- Example applications

- Diagnostic and logging views

### Stage 5 – Advanced Activities

More technical participants can:

- Modify transformations

- Extend message support

- Create client applications

- Develop FHIR profiles and implementation guides

This approach allows clinical and non-technical attendees to participate while still providing meaningful development opportunities. [Connectathon ideas | Meeting]

# Actions

## Joern Guy Suess

### Infrastructure Investigation

Assess:

- Network accessibility

- Internet connectivity

- DNS requirements

- Cloud-hosting options

- Service accessibility for attendees

### Participant Environment Assessment

Determine:

- Laptop constraints

- Queensland Health restrictions

- Availability of Docker or local development tools

- Development options available to participants

### Technical Architecture

Develop a proposed architecture for:

- HL7v2 submission

- Message processing

- Diagnostics and logging

- FHIR transformation

- Data visualisation

### Workshop Assets

Prepare:

- Source code examples

- Deployable services

- Tutorial materials

- Hosted demonstration environment

### Information Sharing

Publish useful outputs and findings into the Track 2 collaboration area. [Connectathon ideas | Meeting]

## Daniel Foulkes

### Direction and Governance

- Engage with Jim regarding track direction.

- Escalate concerns around leadership and ownership.

- Clarify expected outcomes and priorities.

### Learning Design

- Refine the teaching workflow.

- Elaborate candidate use cases.

- Support implementation guide and profiling activities. [Connectathon ideas | Meeting]

## Paul Davies

### Queensland Health Engagement

- Develop imaging and RIS-related concepts.

- Provide Queensland Health perspective on value and relevance.

- Help refine use cases likely to attract participant engagement. [Connectathon ideas | Meeting]

# Risks and Open Questions

## Track Ownership

Responsibility for driving the overall track remains unclear.

The group agreed this should be resolved quickly to avoid delivery risk. [Connectathon ideas | Meeting]

## Connectathon Scope

Questions remain regarding:

- Whether Provider Directory should remain the primary focus.

- Which use case offers the greatest value to Queensland Health.

- How much technical depth is appropriate for the anticipated audience. [Connectathon ideas | Meeting]

## Infrastructure Readiness

Successful delivery depends on:

- Reliable hosted services.

- Sufficient network access.

- Participant access to required tools and systems. [Connectathon ideas | Meeting]

# Immediate Next Steps

# Useful Resources Mentioned

- FHIR Patterns Knowledge Base

- HL7v2-to-FHIR Facade Example

- Imaging Integration Patterns

- Track 2 Collaboration Space

Links were shared during the meeting discussion. [Connectathon ideas | Meeting]

Prepared from the transcript of Connectathon ideas. [Connectathon ideas | Meeting]

| Owner | Action |
| --- | --- |
| Daniel | Discuss direction and ownership with Jim |
| Joern | Investigate infrastructure and deployment options |
| Paul | Elaborate imaging/RIS and service-oriented use cases |
| Team | Hold a follow-up planning session |
| Team | Select final tutorial scenario |
| Team | Confirm minimum viable Connectathon implementation |